## Sheet1
ID | User Story | Story tasks | Sprint number | Sprint goal | Story type | Story Points | Story Points Completed | Names and Contribution Percentage
3 | As a registered user, I want to be able to create my own chat room so that I can talk with friends in private. | Implement creating/using chatrooms | 3 | User may create chatrooms | F, T | 3 | 3 | Nick 100%
|  | Implement "My Rooms" to save chat rooms | 3 | Allow user to save chat rooms to join easily join later | F, T | 1 | 1 | Nick, 50%. Clark, 50%
7 | As a registered user, I want to be able to appear offline so that I won't be disturbed. | Implement offline functionality to chatrooms | 3 | User will be offline in the chat when they leave the chatroom | F, T | 2 | 2 | Nick, 33%, Clark, 33%, Aidan, 33%
|  | Appear offline if app is closed | 3 | When user closes app, appear offline to friends | NF, T, KA | 1 | 0
|  | Code profile page for user | 3 | Allow user profiles, Show online/offline status on profile page | F, T, KA | 1 | 0
14 | As a registered user, I want to be notified when a new user joins the chat so that I can greet them. | Implement message when another user joins a chatroom | 3 | Show message in chat that a new user has joined | F, T | 2 | 2 | Nick, 100%
1 | As an unregistered user, I want to be able to view chat rooms near me so that I can talk to people in my community. | Implement number of chatrooms before signup | 3 | Allow user to see # of chatrooms near them before signup | F, T | 2 | 2 | Nick, 100%
|  | Register before chatting | 3 | User must register to join the chats near them | F, T | 1 | 1 | Nick, 100%
12 | As a registered user, I want to be able to view who’s online so that I know who I can chat with. | Design UI for friends list | 3 | Mockup UI for friends tab | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement a friends list | 3 | Allow user to add/remove friends | F, T, KA | 1 | 0
|  | Implement which friends are online | 3 | Show which friends are online/offline | F, T | 1 | 1 | Nick, 33%. Clark, 33%. Aidan, 33%
8 | As a registered user, I want to be able to see a short list of users when I hover over a chat so that I can see if I know anyone. | Design UI for listing who's in a chatroom. | 3 | Mockup UI for who is currently in a chatroom before joining | F, T, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement list showing chatroom occupants after joining | 3 | Show a list of chatroom occupants after user joins | F, T | 1 | 1 | Nick, 50%. Clark, 50%
|  | Implement list showing chatroom occupants before joining. | 3 | Show chatroom occupants by hovering over the chatroom | F, T | 1 | 0