## Sheet1
ID | User Story | Story tasks | Sprint number | Sprint goal | Story type | Story Points | Story Points Completed | Names and Contribution Percentage
7 | As a registered user, I want to be able to appear offline so that I won't be disturbed. | Implement offine functionality to chatrooms/friends list | 5 | User will be offline in the chat when they leave the chatroom | F, T | 2 | 2 | Nick, 33%, Clark, 33%, Aidan, 33%
|  | Appear offline if app is closed | 5 | When user closes app, appear offline to friends | NF, T, KA | 1 | 1 | Nick, 100%.
|  | Code profile page for user | 5 | All user profiles, Show online/offline statues on profile page | F, T, KA | 2 | 2 | Nick, 25%, Stephen 25%, Clark, 25%. Aidan, 25%
12 | As a registered user, I want to be able to view who’s online so that I know who I can chat with. | Design UI for friends list | 5 | Mockup UI for friends tab | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement adding friends | 5 | Allow user to add friends and show their online status | NF, T | 1 | 1 | Nick, 33%. Clark, 33%. Aidan, 33%.
|  | Implement online status of friends | 5 | Show user who's online on their friends list | F, T | 1 | 1 | Nick, 100%.
9 | As a registered user, I want to receive chat notifications so that I can respond back promptly to friends. | Design UI for notifications | 5 | Show user a notification when a chats been updated | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement notification UI | 5 | Add UI to notify user of chat updates | F, T | 1 | 1 | Nick, 50%. Clark, 50%.
|  | Implement in app notifications | 5 | Show user notifications for incoming chats or chatroom updates | NF, T | 2 | 2 | Nick, 50%. Clark, 50%.
6 | As a registered user, I want to be able to filter my seach for chat rooms using keywords so that I can find where I belong | Design UI for search filter | 5 | Mockup UI to search for keywords for nearby rooms | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement search filter | 5 | Allow user to search for nearby chatrooms by keywords | F, T | 1 | 1 | Nick, 100%
5 | As a registered user, I want the ability to delete previous messages that I sent in case that I mistakenly wrote the wrong chat. | Design UI for deleting messages | 5 | Mockup UI to delete messages | F, KA | 1 | 1 | Aidan, 20%. Clark, 20%. Stephen, 20%. Joe, 20%. Nick, 20%
|  | Implement functionality to delete messages | 5 | Allow user to delete a message after they sent it | F, T | 1 | 1 | Nick, 50%. Clark, 50%.
10 | As a registered user, I want to be able to paste GIFs in chat so that I can reference funny memes. | Implement sending GIFs | 5 | Allow the user to send a GIF as a message | F, T | 1 | 1 | Nick, 50%. Clark, 50%.
13 | As a registered user, I want to be able to set language filters for my chat rooms so that I can limit explicit language. | Implement language filter as default | 5 | Allow system to filter out explicit language by default | F, T | 1 | 1 | Nick, 50%. Clark, 50%